⚠  SUPERSEDED — original v1 planning document, kept for history.

The as-built system and current roadmap live in the v2 documents (BRD v2, Dev Plan v2, Documentation v2). This v1 file reflects the original Supabase / Vercel plan and should not be used as the source of truth.

As-built stack: Better Auth + self-hosted PostgreSQL 17 + MinIO on Coolify, with Cloudflare DNS — not Supabase / Vercel / Namecheap.

Current roadmap order: all remaining features first → Payment system (final build phase) → AI input validator (after payment, the last item).

WUDUH

وضوح

Development Plan & Execution Roadmap

| Document | Development Plan v1.0 |
| --- | --- |
| Product | Wuduh — Feasibility Study Builder |
| Date | June 2026 |
| Stack | Next.js · Supabase · Vercel · Puppeteer |
| Timeline | 8 weeks to MVP · 16 weeks to V2 |
| Status | Ready to hire · Ready to build |

# 1. What You Already Have

Before a single line of code is written, Wuduh has more foundation than most products have after six months of development. This section documents everything that is ready for a developer to pick up immediately.

## 1.1 Strategy & Business

- Product documentation (20 pages) — what the product is, how it evolved, every decision recorded

- Business Requirements Document (26 pages) — full technical specification, database schema, API endpoints, feature requirements

- Pitch deck (10 slides) — investor-ready, Navy/Gold brand, all key sections

- Validation plan — who to talk to, what to ask, how to measure success

- B2B2C go-to-market — accelerator targets identified (Monshaat, Flat6Labs, KAUST, Badir, STC/Aramco)

## 1.2 Product & Design

- Card journey — all 52 cards designed, sequenced, and specified across 8 sections

- Card config file (wuduh-cards.json) — 184KB of production-ready card content in Arabic and English, every prompt, hint, example, and table column defined

- Design system (Wuduh_Design_System.zip) — full component library, color tokens, typography tokens, spacing tokens, SVG assets, UI kit

- Interactive card UI prototype — built and working, all 52 cards navigable

- Landing page design — built and working, full wuduh.app homepage

- PDF export template — designed and built, paper surface, geometric watermark, all 8 sections

- Logo — Direction B (Threshold / arch mark) selected, pending final refinement from designer

## 1.3 What Is Ready to Hand to a Developer Today

✅  A developer who receives all of the above can start Phase 1 on day one without a single clarification meeting. The BRD answers every technical question. The card config answers every content question. The design system answers every visual question.

# 2. Before Development Starts

Three things must happen before a developer writes a single line. Each one is a blocker for quality — not optional.

## 2.1 Hire Your Technical Partner

This is the most important decision of the next 30 days. The wrong developer costs more than no developer.

| Path | Timeline | Cost | Best For |
| --- | --- | --- | --- |
| Technical co-founder | 2–4 weeks to find | Equity only | If you have time to find the right person — this is the best outcome |
| GCC freelance developer | 1–2 weeks to hire | SAR 11,000–30,000 | If you want local, Arabic-speaking, culturally aligned |
| Remote freelance developer | 3–5 days to hire | SAR 7,500–18,000 | If speed matters more than location — strong Next.js pool globally |
| Development agency | 2–3 weeks to contract | SAR 37,000–90,000 | If you need structure, PM support, and can afford the premium |

⚠  Send every candidate the BRD before any conversation. Ask them: 'Read Section 5 and tell me how you would implement auto-save and RTL layout.' The answer tells you everything.

### Developer Red Flags — Walk Away If:

- They cannot explain how they would implement auto-save without asking for more detail

- They have never worked with Arabic RTL layouts and are not concerned about it

- They suggest building a native mobile app instead of a responsive web app for the MVP

- They want to skip Supabase Row Level Security because it is 'complicated'

- They want to start building before reading the BRD

- They cannot give a fixed price or a realistic estimate range after reading the spec

## 2.2 Validate Before You Build

You have not shown this to a real founder or accelerator yet. Do not skip this step.

| Who | How Many | What to Show | What to Ask |
| --- | --- | --- | --- |
| First-time Saudi founders | 5 people | The interactive card UI prototype built in this session | Where do you hesitate? Would you use this? Would you pay for it? |
| Accelerator program managers | 3 people | The pitch deck + PDF export template | How do your founders currently prepare studies? Would you pay for this per cohort? |
| Saudi investors (optional) | 1–2 people | The PDF export template | Would you take a study that looked like this seriously? |

ℹ  Where to find founders: Twitter/X Saudi startup community, Indie Hackers, Reddit r/startups, LinkedIn. Where to find accelerator contacts: Monshaat website, Flat6Labs LinkedIn, KAUST Entrepreneurship page.

⚠  Target timeline for validation: 2–3 weeks. If founders complete the card UI prototype and say 'I would use this', start development. If they do not, understand why before spending money on code.

## 2.3 Get Three Things Ready Before Day One of Development

- Register wuduh.app domain (or wuduh.sa) — do this today, costs SAR 60/year

- Create Supabase project at supabase.com — free, takes 5 minutes, gives you the database URL the developer needs on day one

- Create Vercel account at vercel.com — free, link it to a GitHub account, ready for the developer to deploy to

✅  These three setup tasks cost SAR 60 and 20 minutes. Without them, the developer spends day one on setup instead of building.

# 3. Development Phases

The MVP is 8 weeks of focused development. Everything below is derived directly from the BRD. Phases are sequential — each one unlocks the next.

Phase 1  Foundation  ·  Weeks 1–2

Goal: A working skeleton with authentication, database, and RTL switching. Nothing the founder sees yet — pure infrastructure.

### What Gets Built

- Next.js project initialized with Tailwind CSS and IBM Plex font stack from Google Fonts

- Supabase project configured — auth, database tables, storage buckets, Row Level Security policies

- All 4 database tables created: profiles, studies, answers, exports (see BRD Section 4)

- User registration and login with email confirmation

- RTL/LTR root-level switching — `dir='rtl'` applied globally when Arabic is selected

- Basic dashboard shell — no real data, just the layout and navigation structure

- Vercel deployment pipeline — every push to main deploys automatically

- Environment variables configured — Supabase URL, anon key, service role key

### Deliverables at End of Phase 1

- Developer can log in and log out

- Database schema matches BRD Section 4 exactly

- RTL layout switches correctly when language is changed

- App deploys to Vercel on every commit

🚨  Row Level Security must be configured before any data is written. A founder must only be able to read and write their own studies. This is not optional — it is a security requirement.

Phase 2  Card Engine  ·  Weeks 3–5

Goal: All 52 cards working with real content from wuduh-cards.json, auto-save, progress tracking, and hint system. This is the core of the product.

### What Gets Built

- Card config loader — reads wuduh-cards.json and renders the correct card type for each entry

- Text card component — multi-line textarea with character counter, auto-save on blur

- Table card component — repeatable rows, add/delete row, column headers from config

- Upload card component — file picker, preview, upload to Supabase Storage, URL saved to answers table

- Language select card (C0) — two-option selector, saves to user profile and study record

- Swipe right / Complete mechanic — marks answer status as 'done', advances to next card

- Swipe left / Skip mechanic — marks answer status as 'skipped', advances to next card

- Auto-save — every card action writes to the answers table immediately, no manual save

- Progress bar — calculates mandatory cards completed vs total mandatory, displays in header

- Section stepper — shows which section is active, how many cards are done per section

- Section overview screen — shows all cards per section with status, allows jumping to any card

- Resume — on login, founder returns to the last incomplete card automatically

- Hint system — hint icon on every card, expands inline panel, content from card config

- Logo upload — card C1, stores in Supabase Storage, previews in the card

- Mobile responsive — test on 375px viewport throughout, fix layout issues as they appear

### Developer Notes for Phase 2

- Load wuduh-cards.json as a static import — do not put cards in the database, the config file is the source of truth

- The answers table stores JSONB — text cards store a string, table cards store an array of objects, upload cards store a URL string

- Auto-save must be idempotent — saving the same answer twice must update, not duplicate

- Test the card sequence on mobile touch devices, not just desktop — swipe gestures must feel natural

### Deliverables at End of Phase 2

- All 52 cards render correctly in English

- Founder can complete, skip, and revisit every card

- Progress saves correctly if the browser is closed and reopened

- Hint opens and closes on every card

- Works correctly on iPhone Safari and Android Chrome

⚠  Phase 2 is the longest phase and the highest risk for scope creep. The developer must build exactly what is specified — no additional features, no design improvements, no V2 features. Ship the 52 cards first.

Phase 3  PDF Export  ·  Weeks 6–7

Goal: A founder clicks Export and receives a professional PDF that looks like it cost SAR 5,000 to produce. This is the product's core promise.

### What Gets Built

- HTML study template for English (LTR) — paper surface, geometric watermark, arch mark header, all 8 sections

- HTML study template for Arabic (RTL) — identical structure, RTL layout, Arabic fonts, flipped direction

- Puppeteer serverless function on Vercel — receives study_id, fetches all answers, renders HTML template, returns PDF binary

- Cover page — founder logo, startup name, founder name, date, language, study status

- Section pages — each of the 8 sections with the founder's answers formatted professionally

- Competitor table renderer — repeatable table rows formatted as a clean comparison table in the PDF

- Team table renderer — same mechanic as competitor table

- Risk table renderer — includes High/Medium/Low likelihood pills with semantic colors

- Incomplete disclaimer — auto-injected when mandatory cards are skipped, gold left-border callout

- Export history — every export saved to the exports table with a timestamp and PDF URL

- Re-download — founder can access previous exports from the dashboard

### Developer Notes for Phase 3

- Build and test the HTML template in a browser first — make it look perfect before connecting Puppeteer

- The paper surface color is #FAF7F0, the geometric watermark is navy at 10% opacity

- Arabic font: IBM Plex Sans Arabic from Google Fonts — load it in the HTML template head

- English font: IBM Plex Serif for headings, IBM Plex Sans for body, IBM Plex Mono for labels

- PDF download URL expires after 1 hour — regenerate on demand rather than storing permanently

- Test the export with a fully complete study AND with a study that has 30% of cards skipped

### Deliverables at End of Phase 3

- English PDF export downloads and looks professional on desktop and mobile

- Arabic PDF export is fully RTL and uses the correct fonts

- Incomplete study disclaimer appears correctly for skipped mandatory cards

- Export completes in under 10 seconds

- Previous exports are accessible from the dashboard

⚠  Build the English template first, test it exhaustively, then build Arabic. Do not try to build both simultaneously — the RTL PDF is significantly more complex and must be treated as a separate deliverable.

Phase 4  Polish & Launch  ·  Week 8

Goal: The product works correctly for real users. Not perfect — correct. Every user flow works end to end. Ship it.

### What Gets Built

- End-to-end testing of all 4 user flows from the BRD (new founder, returning founder, skipped cards, incomplete export)

- Cross-browser testing — Chrome, Safari iOS, Firefox, Samsung Internet

- Mobile device testing — real iPhone and Android, not just browser DevTools

- Performance check — page load under 2 seconds, auto-save under 500ms, PDF under 10 seconds

- Security review — confirm RLS policies are correct, file upload validation is server-side

- Error monitoring — Sentry free tier configured, basic error tracking live

- Analytics — Plausible or Vercel Analytics, privacy-friendly, no cookie banner needed

- Custom domain — wuduh.app connected to Vercel deployment

- Arabic copy review — native Arabic speaker reviews all card text and hints for natural register

### Deliverables at End of Phase 4 — MVP Launch Criteria

🚨  Do not launch until every item below is true. Launch with a broken product and you lose the founder's trust permanently.

- A real founder can sign up, complete a study, and export a PDF without any assistance

- The PDF looks professional enough that a founder is not embarrassed to send it

- Auto-save works — no founder loses their answers due to a session expiry or browser close

- RTL Arabic layout works correctly on mobile Safari

- The app loads in under 2 seconds on a 4G connection

- Sentry is capturing errors

- The domain resolves correctly and HTTPS is active

# 4. Full Timeline — 16 Weeks

| Week | Phase | Key Activity | Milestone |
| --- | --- | --- | --- |
| Week 0 | Pre-build | Hire developer, validate with 5 founders + 3 accelerators, set up Supabase + Vercel + domain | Developer hired. Validation complete. Infrastructure ready. |
| Week 1 | Phase 1 | Next.js setup, Supabase config, database schema, RLS policies | Database live. Auth working. |
| Week 2 | Phase 1 | RTL switching, dashboard shell, Vercel deployment pipeline | App deploys. RTL switches. |
| Week 3 | Phase 2 | Card config loader, text card component, upload card component | First card renders with real content. |
| Week 4 | Phase 2 | Table card component, swipe mechanics, auto-save | All card types working. Auto-save confirmed. |
| Week 5 | Phase 2 | Progress tracking, section stepper, hint system, resume on login, mobile testing | Full 52-card journey works on mobile. |
| Week 6 | Phase 3 | HTML export template (English), PDF styling, section formatting | English PDF looks professional in browser. |
| Week 7 | Phase 3 | Puppeteer serverless function, Arabic PDF template, export history | Both languages export correctly. |
| Week 8 | Phase 4 | End-to-end testing, error monitoring, analytics, domain, Arabic copy review | MVP live at wuduh.app. |
| Weeks 9–10 | Post-launch | First real users onboarded. Bug fixes only. Collect feedback. | 10 real founders have completed a study. |
| Weeks 11–12 | V2 Planning | Analyse feedback. Prioritise V2 features. Plan financial engine and AI validator. | V2 spec confirmed. |
| Weeks 13–16 | V2 Build | AI input validator, financial projections engine, theme gallery, accelerator white-labeling | V2 live. |

# 5. Decisions to Make Before Day One of Development

These are not optional. Every item below is a blocker for development if left unresolved past week 0.

| Decision | Options | Recommendation | Deadline |
| --- | --- | --- | --- |
| Technical partner | Co-founder / GCC freelancer / remote freelancer / agency | GCC freelancer or remote freelancer with Next.js + Supabase experience | Before Week 1 |
| Domain | wuduh.app / wuduh.sa / wuduh.co | wuduh.app — globally readable, professionally registered | This week |
| PDF generation | Puppeteer / React-PDF / PDFKit | Puppeteer — only option that handles Arabic RTL reliably | Before Week 6 |
| Payment gateway (V2 prep) | Moyasar / Stripe / HyperPay | Moyasar — supports MADA, required for Saudi market | Before V2 |
| Arabic copywriter | Freelance native Arabic speaker | Hire before Phase 2 ends — 52 card texts + 52 hints to review | Before Week 5 |
| Error monitoring | Sentry / LogRocket / none | Sentry free tier — non-negotiable for a product handling real data | Before Week 8 |
| Analytics | Plausible / Vercel Analytics / Google Analytics | Plausible — privacy-friendly, no cookie banner, GDPR-safe | Before Week 8 |
| Logo finalisation | Direction B (Threshold arch) selected — needs bold refinement | Request 20% bolder stroke weight + favicon/app icon test from designer | Before Week 6 (PDF template needs it) |

# 6. Budget Summary

## 6.1 One-Time Development Costs

| Item | Low Estimate | High Estimate | Notes |
| --- | --- | --- | --- |
| Developer (8 weeks MVP) | SAR 7,500 | SAR 37,500 | Remote freelancer to GCC freelancer range |
| Arabic copywriter | SAR 1,125 | SAR 3,000 | Review 52 cards + 52 hints in Arabic — native speaker only |
| PDF export designer | SAR 1,875 | SAR 5,625 | Finalize PDF template design for handoff to developer |
| Logo finalisation | SAR 375 | SAR 1,500 | Minor refinement to Direction B mark — bolder stroke, favicon |
| Domain registration | SAR 60 | SAR 225 | wuduh.app or wuduh.sa — annual cost |
| TOTAL MVP | SAR 10,935 | SAR 47,850 | All-in to launch |

★  If you find a technical co-founder willing to work for equity, the total MVP cost drops to SAR 3,435–10,350 (copywriter + designer + domain only). This is the lowest-risk path if you have time to find the right person.

## 6.2 Monthly Infrastructure Costs

| Service | Free Until | Cost After | MVP Expectation |
| --- | --- | --- | --- |
| Vercel | 100GB bandwidth/month | SAR 75/month | Free tier sufficient for first 6 months |
| Supabase | 500MB database / 1GB storage | SAR 94/month | Free tier sufficient for first 500 studies |
| Sentry | 5,000 errors/month | SAR 97/month | Free tier sufficient for MVP |
| Plausible Analytics | None — paid from day one | SAR 75/month | Optional — use Vercel Analytics free instead |
| Resend (email) | 3,000 emails/month | SAR 75/month | Free tier sufficient for MVP |
| Domain renewal | Annual | SAR 60/year | Negligible |
| TOTAL | First 6 months likely free | SAR 341–416/month | After free tiers are exceeded |

## 6.3 V2 Additional Costs

| Item | Estimate | Notes |
| --- | --- | --- |
| Developer (8 weeks V2) | SAR 7,500–37,500 | Same developer or new hire for V2 features |
| AI validator integration | SAR 375–1,500/month | Claude API usage — depends on volume |
| Moyasar payment gateway | 2.9% + SAR 1.12 per transaction | No setup fee — pay per transaction |
| White-label design work | SAR 3,750–11,250 | Per accelerator — custom branding for their cohort |

# 7. Your Week 0 Action Plan

This is what you personally do before development starts. Not the developer — you.

## Monday — Tuesday

- Register wuduh.app domain (Namecheap or Google Domains, 10 minutes)

- Create Supabase account and project at supabase.com (5 minutes)

- Create Vercel account at vercel.com and link to a GitHub account (5 minutes)

- Post on Twitter/X and LinkedIn: 'I am building a feasibility study tool for Saudi founders. Looking for a Next.js developer with Supabase experience. DM me.' Include a brief description of the project.

- Post on Mostaql (مستقل) with the BRD attached — ask for fixed-price proposals

## Wednesday — Thursday

- Reach out to 5 first-time Saudi founders on Twitter/X, LinkedIn, or Indie Hackers — ask for 15 minutes to show them the card UI prototype

- Identify 3 program managers at Monshaat, Flat6Labs, and KAUST Entrepreneurship on LinkedIn — send a connection request with a short message

- Review developer proposals — screen with the BRD question (Section 5, how would you implement auto-save and RTL?)

## Friday — Weekend

- Run the first 2–3 founder conversations with the card UI prototype open on your screen

- Shortlist 2–3 developer candidates and schedule video calls for next week

- Prepare a simple Notion page or Google Doc that links to: the BRD, the card config file, the design system zip, and the card UI prototype — this is your developer onboarding packet

✅  By end of Week 0 you should have: a domain registered, infrastructure accounts created, at least 3 founder conversations scheduled, at least 1 accelerator conversation scheduled, and at least 2 developer candidates shortlisted.

# 8. V2 Roadmap — After MVP Validation

V2 is not planned in detail yet — that would be premature. These features are confirmed as next priorities based on the product planning session. The exact sequence and spec will be determined by what MVP users tell us.

| Feature | What It Does | Why It Matters | Phase |
| --- | --- | --- | --- |
| AI input validator | Flags bad data and surfaces contradicting evidence in real time as the founder types | Turns Wuduh from a formatting tool into a thinking partner — the single biggest differentiator | V2 — Q4 2026 |
| Financial projections engine | Break-even calculator, CAC/LTV inputs, auto-generated charts in the PDF export | Makes the Business Model section credible to investors — currently the weakest section of any founder's study | V2 — Q4 2026 |
| Theme gallery | Founder chooses from multiple export themes — different layouts and visual styles | Personalization reduces the 'generic template' feeling of the export | V2 — Q4 2026 |
| Designer marketplace | Connect founder to a real designer for a custom export theme, Wuduh takes commission | Secondary revenue stream with no build cost beyond the marketplace UI | V2 — Q4 2026 |
| Accelerator white-labeling | Accelerator logos and brand colors applied to the export instead of Wuduh branding | Enterprise tier — unlocks significantly higher B2B pricing | V2 — Q4 2026 |
| Living document | Founder can return and update their study as the startup evolves — version history | Solves the retention problem — gives founders a reason to return after export | V2 — Q4 2026 |
| Arabic RTL (full) | Native Arabic experience — RTL card layout, Arabic hints, Arabic PDF | Required before any Saudi accelerator pitch — the language decision is already in the card config | V2 or accelerated if validation demands it |
| Documentation hub | Ongoing founder workspace — decisions, pivots, meeting notes, milestones | Transforms Wuduh from a one-time tool into a startup OS for early founders | V3 — 2027 |
| Investor shareable link | Live URL the founder shares instead of a PDF — real-time, always current | Modern investor experience — no emailing PDFs | V3 — 2027 |
| API for accelerators | Embed Wuduh into existing accelerator platforms via API | Removes the need for accelerators to adopt a new tool — meets them where they are | V3 — 2027 |

# 9. Success Metrics

These are the numbers that tell you whether the product is working. Measure them from day one.

## 9.1 MVP Success — First 30 Days After Launch

| Metric | Target | Why It Matters |
| --- | --- | --- |
| Founders who complete the full journey | At least 10 | Proves the card UX does not cause drop-off |
| Export rate (% of completers who export) | Above 80% | Proves the export is the goal, not just browsing the cards |
| Founder NPS score (would you recommend?) | Above 40 | Proxy for product-market fit at this stage |
| Accelerator meetings booked | At least 3 | First signal of B2B2C viability |
| Median completion time | Under 90 minutes | Proves the journey is not overwhelming |
| Drop-off card | Identify the top 3 cards where founders stop | Tells you what to fix first in V2 |

## 9.2 Revenue Milestone — First 90 Days

| Milestone | Target | Trigger |
| --- | --- | --- |
| First paying founder | SAR 99–149/study | Within 30 days of launch |
| First accelerator pilot agreement | SAR 1,500–5,000/cohort | Within 60 days of launch |
| MRR from direct founders | SAR 1,500/month | By day 90 |
| First cohort deployed through an accelerator | 20+ founders | By day 90 |

🚨  If none of these milestones are hit by day 90, do not build V2 until you understand why. The problem is not the product — it is either distribution (how founders find you) or value (what they get from it). Fix one before building more.

# 10. Complete Deliverable Inventory

Everything produced in the planning session, ready to hand to a developer, investor, or accelerator today.

| Deliverable | Format | Status | Hand To |
| --- | --- | --- | --- |
| Product Documentation | Word (.docx) | Complete — 20 pages | Developer / Investor / Accelerator |
| Business Requirements Document | Word (.docx) | Complete — 26 pages | Developer (primary) |
| Pitch Deck | PowerPoint (.pptx) | Complete — 10 slides | Investor / Accelerator |
| Card Config File | JSON (.json) | Complete — 52 cards, bilingual | Developer (primary) |
| Design System | ZIP archive | Complete — components, tokens, SVGs, UI kit | Developer (primary) |
| Interactive Card UI | Live prototype | Complete — all 52 cards navigable | Founders for validation |
| Landing Page | Live prototype | Complete — full wuduh.app homepage | Accelerators / Investors |
| PDF Export Template | Live prototype | Complete — all 8 sections, paper surface | Investors for validation |
| Logo Direction | Image | Direction B selected — refinement needed | Designer for final polish |
| Brand Identity Prompt | Text | Complete — ready for designer | Designer |
| Development Plan | This document | Complete | Developer / You |
| Validation Plan | In BRD Section 9 | Complete — scripts and targets defined | You to execute |

Wuduh — Development Plan v1.0 — June 2026 — Confidential